## Sheet1
| DATE | TIME | WHO | WHAT | WHERE
WEEK 1 | 2024-01-08 | 6:00 - 6:45pm | PARENTS, CAST, CREW, PIT MANDATORY | PARENT INFO MEETING - MANDATORY | Auditorium
|  | 6:45 - 9:00pm | CAST - Crew/Pit (optional) | Read/Sing Through of show
WEEK 2 | 2024-01-15 | NO RHEARSAL - MLK DAY
| 2024-01-16 | 6:00 - 9:00pm | COSTUMES ONLY | Discuss Costume Plot/Plan | Auditorium
| 2024-01-17 | 6:00 - 9:00pm | COSTUMES/HAIR/MAKEUP ONLY | Discuss Costume/Hair/Makeup
Week 3 | 2024-01-22 | 6:00 - 8:30pm | COSTUMES optional | Start pulling from our costume closet/determine what needs to get bought. Get measurements from cast. | Auditorium
| 2024-01-23 | 6:00 - 8:30pm | COSTUMES optional
| 2024-01-24 | 6:00 - 8:30pm | COSTUMES optional
| 2024-01-25 | 6:00 - 8:30pm | COSTUMES optional
| 2024-01-26 | 6:00 - 8:30pm | COSTUMES optional
Week 4 | 2024-01-29 | 6:00 - 8:30pm | COSTUMES optional | Continue to costume gather | Auditorium
| 2024-01-30 | 6:00 - 8:30pm | COSTUMES optional
| 2024-01-31 | CURRICULUM NIGHT
| 2024-02-01 | 6:00 - 8:30pm | COSTUMES optional
Week 5 | 2024-02-05 | 6:00 - 8:30pm | COSTUMES optional |  | Auditorium
| 2024-02-06 | 6:00 - 8:30pm | COSTUMES | Continue to fit/try on
| 2024-02-07 | 6:00 - 8:30pm | COSTUMES
| 2024-02-08 | NO REHEARSAL/VARIETY SHOW
Week 6 | 2024-02-12 | 6:00 - 9:00pm | Crew optional |  | Auditorium
| 2024-02-13 | 6:00 - 9:00pm | Costumes. Crew optional | costume/try on K-5 kids
| 2024-02-14 | 6:00 - 9:00pm | Costumes. Crew optional
| 2024-02-15 | 6:00 - 9:00pm | Crew optional
Week 7 | 2024-02-19 | 6:00 - 9:00pm | ALL optional | First Spring Break | Auditorium
| 2024-02-20 | 6:00 - 9:00pm | ALL optional
| 2024-02-21 | 6:00 - 9:00pm | ALL optional
| 2024-02-22 | 6:00 - 9:00pm | ALL optional
Week 8 | 2024-02-26 | 5:30 - 9:00pm | ALL CREW | RUN SHOW | Auditorium
| 2024-02-27 | 5:30 - 9:00pm | ALL CREW | RUN SHOW
| 2024-02-28 | 5:30 - 9:00pm | ALL CREW | RUN SHOW
| 2024-02-29 | 5:30 - 9:00pm | ALL CREW | RUN SHOW
| 2024-03-02 | 10am - 6:00pm | ALL CREW | SET BUILD
Week 9 | 2024-03-04 | 5:30 - 9:00pm | ALL CREW | RUN SHOW + SOUND/LIGHTS | Auditorium
| 2024-03-05 | 5:30 - 9:00pm | ALL CREW | RUN SHOW + SOUND/LIGHTS
| 2024-03-06 | 5:30 - 9:00pm | NO REHEARSAL
| 2024-03-07 | 5:30 - 9:00pm | ALL CREW | RUN SHOW + SOUND/LIGHTS
Week 10 | 2024-03-11 | 4:30 - 9:30pm | ALL CREW | RUN SHOW COMPLETE | Auditorium
| 2024-03-12 | 4:30 - 9:30pm | ALL CREW | RUN SHOW COMPLETE
| 2024-03-13 | 4:30 - 9:30pm | ALL CREW | RUN SHOW COMPLETE
| 2024-03-14 | 4:30 - 9:30pm | ALL CREW | RUN SHOW COMPLETE
SHOW | 2024-03-15 | 5:00 - 10:30pm | OPENING NIGHT!!!!! 5:00 call, 7:00pm start |  | AUDITORIUM
NIGHTS! | 2024-03-16 | 5:00 - 10:30pm | NIGHT #2!!!!! 5:00 call, 7:00pm start |  | AUDITORIUM
| 2024-03-17 | 12:00 - 6pm | CLOSING MATINEE! Call 12:00pm, 2pm start |  | AUDITORIUM
STRIKE SET following show